Beacon Help Module

Implementation Guide

Version 1.0  |  April 2026

Mutual-aid engine for requesting help, offering help, reconnecting missing people and animals, and building a public library of neighbors helping neighbors. 7 spec waves, 45+ tasks, 6 execution phases.

Audience: Development team (agents and humans)

Prerequisites: Community module Phases 2-3 complete (identity, legal, messaging, contacts)

# Community Plan Safety Audit

Before building the Help module, the Community implementation plan was audited for executability and safety. Key findings:

Confirmed Safe

Dependency chain is correct: identity/legal (Phase 2) before messaging/contacts (Phase 3) before groups/equipment (Phase 4) before mesh (Phase 5) before history (Phase 6)

Parallel execution pairs are truly independent: Wave D (messaging) shares no write paths with Wave F (contacts)

CONFolder schema covers all 9 dimensions with NR for non-relevant fields

32 CONFolders created with accurate bookmark statuses reflecting actual completion state

Risks Identified & Mitigations

4 CONFolders blocked on vendor decisions (selfie capture, face match, background check, account creation auth provider). Mitigation: use AWS Textract + Rekognition as MVP defaults, swap vendors later via abstraction layer.

No load testing plan for messaging during mass-casualty events. Mitigation: add load test task to Wave D with target of 10K concurrent threads.

Data deletion cascade (C-05) has no test plan for verifying complete anonymization. Mitigation: add integration test that creates full user dataset, runs deletion, and verifies no PII remains in any table.

Mesh networking (Wave E) has no hardware testing plan. Mitigation: add BLE/WiFi Direct test harness task using physical device lab or emulator grid.

13 placeholder CONFolders need population before Phase 4 begins. Mitigation: schedule CONFolder population sprint between Phases 3 and 4.

The community plan is executable as-is with the above mitigations applied. No blocking structural issues.

# 1. Design Principles

Four principles govern every Help module decision:

No shaming. Users who swipe away a help request are never exposed. The requester never knows who declined. Swipe-away data is device-local only, never transmitted to servers.

Safety-first mutual aid. Location recording begins the moment someone accepts a help request. Both parties' locations are logged every 60 seconds until resolution. This protects everyone involved.

Verified vs Trusted distinction. Trusted neighbor = pre-emergency relationship you chose. Verified neighbor = any ID-verified Beacon user near you who adds legitimacy to geofenced requests. Different badges, different purposes.

Encouragement over obligation. The main feed shows people stepping up. Hearts on stories. A public library of moments that remind people what it means to be human. The goal is to inspire, not guilt.

# 2. Execution Phases

The Help module depends on Community foundations. Build order reflects these dependencies.

| Phase | Waves | What Ships | Depends On |
| --- | --- | --- | --- |
| Phase 1 | N/A | Wait for Community Phases 2-3 | Community identity, legal, messaging, contacts |
| Phase 2 | HA + HB | Request lifecycle + routing + notifications | Community Phase 2-3 complete |
| Phase 3 | HC + HD | Feed, hearts, stories library (parallel) | Phase 2 (requests exist) |
| Phase 4 | HE | Missing people & animals | Phase 2 (feed infrastructure) |
| Phase 5 | HF | Verified/trusted neighbor extensions | Community contacts module |
| Phase 6 | HG | Admin dashboard, moderation, analytics | Can begin Phase 3 for moderation |

# 3. Phase 2: Help Request Core

Foundation of the mutual-aid system. Two waves that must be built together.

## Wave HA: Help Request Lifecycle

| Task | Build | Decisions |
| --- | --- | --- |
| HA-01 | Two entry points: map tag (long-press) + help page form. Categories: welfare check, supply run, transport, medical assist, pet care, shelter, debris, utility, other. | Max active requests per user. Photo attachments. |
| HA-02 | help_requests table: id, requester_id, category, title, description, urgency, status, location, radius_m, timestamps. | Auto-expire policy (72h non-critical). |
| HA-03 | State machine: open > claimed > ongoing > resolved. Also: expired, cancelled. Only requester resolves. | Auto-resolve for abandoned requests. |
| HA-04 | Helper claims request. First-claim for 1:1. Multiple responders for open requests. | Claim timeout (2h) if helper doesn't follow through. |
| HA-05 | Location recording: both parties GPS every 60s from accept to resolution. help_location_log table. Consent prompt. | Recording frequency. 90-day retention. |
| HA-06 | Non-critical expire 72h. Critical escalate to nearby admins. Archive expired. | Escalation chain for unclaimed critical. |

Database tables:

help_requests: id, requester_id, category, title, description, urgency (low/med/high/critical), status (open/claimed/ongoing/resolved/expired/cancelled), location (PostGIS point), radius_m, created_at, claimed_at, resolved_at, expires_at

help_claims: id, help_request_id, helper_id, status (active/completed/withdrawn), claimed_at, completed_at

help_location_log: id, help_request_id, user_id, lat, lon, accuracy_m, timestamp

Implementation steps:

Create help_requests, help_claims, help_location_log tables with PostGIS extension

Build request creation form: category selector, description, urgency, location picker

Build map-tag entry point: long-press on map creates pre-filled request with location

Implement state machine with DB-level optimistic locking for concurrent claims

Build location recording service: background GPS at 60s intervals, encrypted storage

Implement consent prompt on first help accept (links to legal release)

Build expiry cron: 72h for non-critical, escalation notification for critical

Write tests: all state transitions, claim race conditions, location recording start/stop

## Wave HB: Help Routing & Notifications

| Task | Build | Decisions |
| --- | --- | --- |
| HB-01 | Dynamic nearby radius: population density + Beacon user density + urgency. Urban 0.5-2km, suburban 2-10km, rural 10-50km. | Census API for density. Geohash grid for user density. |
| HB-02 | Match request category to helper capabilities from equipment/skills/vehicle registries. | Opt-in vs opt-out for capability routing. |
| HB-03 | Settings toggle: 'Open to nearby help requests during emergencies.' Push notification with swipe-away. | Frequency cap (5/hour). DND override for critical. |
| HB-04 | Non-emergency staggered routing: trusted neighbors first (30min), then verified (1h), then general. | Stagger timing. Non-emergency feed visibility. |
| HB-05 | Swipe-away privacy: recorded locally only. Requester sees 'X notified, Y responded' never who declined. | Aggregate analytics only, never per-user. |

Implementation steps:

Build proximity module: Census API integration, geohash user density grid, dynamic radius calculation

Build capability matcher: category-to-capability mapping table, query equipment/skills/vehicles registries

Implement notification routing: staggered delivery (trusted > verified > general), frequency cap

Implement swipe-away privacy: device-local recording only, aggregate-only server analytics

Build settings toggle for help notification opt-in

Test: radius calculation accuracy, capability matching, notification delivery timing, swipe-away zero-leakage

# 4. Phase 3: Feed & Stories (Parallel)

Run Wave HC and Wave HD in parallel. Feed and stories are independent UI concerns.

## Wave HC: Help Feed & Rankings (Window 1)

Build order:

HC-01: Main feed. Tabs: Open, Ongoing, Resolved. Cards: category badge, title, distance, time, status, helper count.

HC-02: Ranking algorithm. Sort by recency (default), urgency, distance, trending. Critical always surfaces above non-critical.

HC-03: Heart system. Anonymous hearts on resolved stories. One per user. Redis counter with DB sync.

HC-04: Prayer requests. Dedicated category, no claiming, no location, distinct styling, 7-day soft expiry.

HC-05: Feed moderation. Report button, auto-hide after 3 flags, moderator queue, appeal process.

## Wave HD: Stories & Public Library (Window 2)

Build order:

HD-01: Story nomination. After resolution, any involved party nominates. All named participants must consent.

HD-02: Story page. Title, narrative, category tags, neighborhood-level location, date, hearts, participants (first name + last initial).

HD-03: Story library. Browse all public stories. Sort by hearts, recency, category, location. Search by keyword.

HD-04: Story takedown. Any participant can remove at any time. Immediate soft delete. No appeal needed.

HD-05: Story moderation. Same pipeline as feed moderation. Shared queue.

# 5. Phase 4: Missing People & Animals

HE-01: Missing person report. Name, photo, last known location, description, medical needs. Verified users only.

HE-02: Missing animal report. Species, breed, name, photo, last known location, collar/microchip info.

HE-03: Found reports. Cross-reference against active missing reports by proximity + description. Auto-notify reporter.

HE-04: Reconnection feed. Dedicated Missing tab within help page. Resolved reports auto-move to stories.

HE-05: Privacy. Missing reports visible to verified users only. Contact exchange through Beacon DM only.

# 6. Phase 5: Verified Neighbor Extensions

HF-01: Verified neighbor badge. ID-verified + within geofence = badge on help responses. Distinct from trusted neighbor.

HF-02: Trusted neighbor geofence request. Broadcast to radius seeking trusted neighbors. Opt-in. Pre-emergency meetups.

HF-03: Meetup coordination. Temporary group with location/time. After meetup, mutual confirmation establishes relationship.

HF-04: Legitimacy scoring. Verified-neighbor responses get priority queue placement on geofenced requests.

# 7. Phase 6: Help Manager in beacon-dev

HG-01: Dashboard. Total requests, response time, category breakdown, geographic heatmap.

HG-02: Moderation queue. Flagged content, moderator actions (dismiss/hide/warn/ban), audit log.

HG-03: Story library admin. Feature/unfeature stories, review takedowns, manage nomination queue.

HG-04: Missing persons admin. Active reports dashboard, escalation tools, wider-radius promotion.

HG-05: Help analytics. Response time, completion rate, helper retention, coverage gaps. CSV export.

# 8. CONFolder Status

15 CONFolders created for the Help module, covering all sub-modules. Combined with the 32 Community CONFolders, the central index now tracks 47 modules.

| Module | Status | Priority | Blocking Issue |
| --- | --- | --- | --- |
| help (top-level) | in-progress | 1 | Finalize liability framework |
| help.requests.lifecycle | in-progress | 1 | Claim race condition handling |
| help.requests.location-recording | in-progress | 1 | Dispute hold policy |
| help.routing.proximity | in-progress | 2 | Census data granularity |
| help.routing.capability | placeholder | 2 | Needs equipment registry first |
| help.routing.notifications | in-progress | 1 | TCPA compliance for SMS |
| help.feed | in-progress | 1 | Polling vs websocket decision |
| help.feed.hearts | in-progress | 3 | None |
| help.feed.prayers | placeholder | 3 | None |
| help.feed.moderation | in-progress | 2 | Appeal process design |
| help.stories | in-progress | 2 | Web accessibility decision |
| help.missing | placeholder | 2 | NamUs/NCIC research |
| help.neighbors.verified | placeholder | 3 | None |
| help.neighbors.trusted-geofence | placeholder | 3 | None |
| help.admin | placeholder | 3 | None |

# 9. Cross-Module Data Flows

Help -> Community

Request creation reads verified badge status (identity)

Helper matching queries equipment/skills/vehicles (equipment)

DM between helper and requester uses messaging backend (messages)

Location recording uses location sharing infrastructure (contacts)

Trusted neighbor requests extend community.contacts.trusted-neighbors

Help -> Map

Help requests can be tagged on map (long-press interaction)

Help request locations shown as map layer during events

Missing person last-known-location plotted on map

Help -> Alerts

Critical unclaimed help requests escalate to alert system

Missing person reports can generate area alerts

# 10. Gate Checks

Phase 2 exit:

Users can create help requests from both map and help page

State machine handles all transitions including concurrent claims

Location recording starts on accept, stops on resolution, encrypted at rest

Notifications reach nearby helpers with correct proximity radius

Swipe-away privacy verified: zero decline data on server

Phase 3 exit:

Feed displays open/ongoing/resolved requests with correct ranking

Hearts increment/decrement correctly under concurrent load

Stories require all-party consent and support instant takedown

Moderation auto-hides after threshold, moderator queue functional

Phase 4 exit:

Missing reports created by verified users, visible to verified users

Found reports cross-reference and auto-notify original reporter

Contact exchange happens through DM only, no public phone numbers

Phase 5 exit:

Verified neighbor badge displays correctly on help responses

Trusted neighbor geofence broadcast works with staggered delivery

Meetup coordination creates and auto-deletes temporary group

Phase 6 exit:

Admin dashboard shows real-time metrics and moderation queue

All admin actions have full audit trail